## Sheet1
Product Backlog (Analytics Project) |  |  | PAI
Priority | As a ... | I need... | Item | Effort Required (Man hours) | Status
Phase (1)
1 | Manager | to understand current fraud patterns and financial impact | Understanding SP-Buy Fraud Landscape | 10 | Done
2 | Data Administrator | to design and implement secure database for order data | Set Up Order Database Schema | 15 | Done
3 | Data Administrator | to build reliable data pipeline for order processing | ETL Pipeline Implementation | 20 | Done
4 | Data Administrator | to ensure data quality and standardization | Data Cleaning & Preprocessing | 15 | Done
5 | Data Scientist | to identify fraud patterns and correlations | Exploratory Data Analysis | 25 | Done
6 | Data Administrator | to create real-time fraud monitoring dashboards | BI Dashboard Development | 20 | Done
7 | Data Translator | to communicate insights to stakeholders | Fraud Analysis Report & Presentation | 10 | Done
8 | Team Lead | to maintain project documentation | Project Documentation | 15 | Done
9 | Team | to collaborate and align on objectives | Team Meetings & Coordination | 10 | Done
Total Hours
140
Phase (2)
10 | Data Scientist | to develop fraud detection model | ML Model Development | 30 | Done
11 | Data Scientist | to hypertune model | Model Optimization | 25 | Done
12 | Data Scientist | to monitor model with monitoring system (Mlflow) | Model Monitoring Dashboard | 20 | Done
13 | Data Translator | to create user guidelines | System Documentation & Training | 10 | Done
14 | Software Developer | to implement alert system | Fraud Alert System | 15 | Done
15 | Software Developer | Designing graphics for UI/UX | Wireframes | 5 | Done
16 | Data Scientist | to conduct advance data processing techniques | Outlier Detection & Imbalanced Classes | 20 | Done
Total Hours
125